## Agilefant Timesheet
Story Id | Story | Task Id | Task | Estimated Effort | Actual Effort
NA | Tasks without a story | 4154 | Planning out solving our Technical Debt problem
NA | Tasks without a story | 4319 | Sprint Planning
NA | Tasks without a story | 4596 | Standup
NA | Tasks without a story | 4153 | TECH-DEBT: Change FeedEvent class to represent multiple users (viewers) per instance.
NA | Tasks without a story | 4160 | TECH-DEBT: Change pagination to be done on the server side, not the client side (Do BEFORE Task:4159)
NA | Tasks without a story | 4159 | TECH-DEBT: Implement pagination on the activities page to prevent time out errors (Do AFTER Task:4160)
NA | Tasks without a story | 4156 | TECH-DEBT: Modify FeedEvent controller, repository and service to generate one FeedEvent per event.
NA | Tasks without a story | 4158 | TECH-DEBT: Resolve error where Header doesn't know which role the user is, so flashes between admin/user header styles
NA | Tasks without a story | 4155 | TECH-DEBT: Resolve warnings thrown by JEST Tests over bootstrap-vue elements
NA | Tasks without a story | 4157 | TECT-DEBT: Modify the GET request for FeedEvent(s) to work with the changes to the DB
424 | U33 - Activity Outcomes | 4357 | Add existByOutcome to ResultRepository and add repository to OutcomeController
424 | U33 - Activity Outcomes | 4328 | Create DELETE endpoint for when deleting an Outcome BACK-END
424 | U33 - Activity Outcomes | 4333 | Create DELETE request for an Outcome when deleting activity FRONT-END
424 | U33 - Activity Outcomes | 4327 | Create PUT endpoint for when updating an Outcome BACK-END
424 | U33 - Activity Outcomes | 4332 | Create PUT request for an outcome when editing activity FRONT-END
424 | U33 - Activity Outcomes | 4799 | Fix mutating props warning, refactor prop name.
422 | U35 - Activity search - (Modified ACs) | 4329 | Add a text search (UI element) by option to the front end (to enter the name in)
422 | U35 - Activity search - (Modified ACs) | 4790 | Add pagination to backend GET endpoint for searching by keyword
422 | U35 - Activity search - (Modified ACs) | 4337 | Add the method in the backend for searching for a activity by activity type (OR)
422 | U35 - Activity search - (Modified ACs) | 4353 | Add the method in the backend for searching for an activity by activity type (AND)
422 | U35 - Activity search - (Modified ACs) | 4350 | Add the method in the backend for searching for an activity by name
422 | U35 - Activity search - (Modified ACs) | 4356 | Create card for displaying activity search results
422 | U35 - Activity search - (Modified ACs) | 4741 | Create new component ActivitySearch.vue STUB
422 | U35 - Activity search - (Modified ACs) | 4742 | Create new component UserSearch.vue
422 | U35 - Activity search - (Modified ACs) | 4352 | Define the search rules for searching for activities by name
422 | U35 - Activity search - (Modified ACs) | 4355 | Implement the GET request for activities by name on the front end
422 | U35 - Activity search - (Modified ACs) | 4354 | Implement the GET request for activity by activity type on the front end
422 | U35 - Activity search - (Modified ACs) | 4789 | Implement the Search Rules into the search by name get endpoint
422 | U35 - Activity search - (Modified ACs) | 4351 | Update the search by name method to do exact match searches
420 | U37 - Map pane | 4728 | Add LocationIO .vue to ActivityForm.vue (Creating and Editing an Activity)
420 | U37 - Map pane | 4725 | Add LocationIO .vue to EditLocation.vue (Edit user/profile)
420 | U37 - Map pane | 4726 | Add MapViewer.vue component to ViewActivity.vue page.
420 | U37 - Map pane | 4597 | Create 'view-only' option in LocationIO.vue
420 | U37 - Map pane | 4582 | Create LocationIO.vue component
420 | U37 - Map pane | 4590 | Create a component MapViewer.vue for only viewing locations on a map (MapViewer.vue)
420 | U37 - Map pane | 4821 | Fix Environment Variable for API Key in GitLab Runner
420 | U37 - Map pane | 4801 | Modify MapViewer to correctly fit to the page it is on (AC1)
420 | U37 - Map pane | 4719 | Research how to add a map component to Vue, write business report
420 | U37 - Map pane | 4722 | Store the GoogleMaps API key as an environment variable in the front end.
420 | U37 - Map pane | 4583 | Toggle visability of map pane in LocationIO component. (LocationIO .vue)
419 | U38 - User Geolocation - (Modified ACs) | 4840 | Add BACK-END UserController endpoint to Edit Location
419 | U38 - User Geolocation - (Modified ACs) | 4588 | Add fields public_location and private_location to User class
419 | U38 - User Geolocation - (Modified ACs) | 4587 | Create Location class on backend.
419 | U38 - User Geolocation - (Modified ACs) | 4729 | Implement EditLocation.vue to use api calls to edit a user's location
419 | U38 - User Geolocation - (Modified ACs) | 4580 | In EditProfile.vue, create a new Component EditLocation. Put component in a tab in EditProfile.vue STUB
419 | U38 - User Geolocation - (Modified ACs) | 4846 | Move the location data for test database from the activity table to the location table