## Agilefant Timesheet
Story Id | Story | Task Id | Task | Estimated Effort | Actual Effort
NA | Tasks without a story | 4596 | Standup | 33.75
NA | Tasks without a story | 4319 | Sprint Planning | 36 | 58
NA | Tasks without a story | 4154 | Planning out solving our Technical Debt problem | 13.5 | 27.3
NA | Tasks without a story | 4153 | TECH-DEBT: Change FeedEvent class to represent multiple users (viewers) per instance. | 1 | 0.5
NA | Tasks without a story | 4160 | TECH-DEBT: Change pagination to be done on the server side, not the client side (Do BEFORE Task:4159) | 2 | 9.2
NA | Tasks without a story | 4159 | TECH-DEBT: Implement pagination on the activities page to prevent time out errors (Do AFTER Task:4160) | 2 | 3.9
NA | Tasks without a story | 4156 | TECH-DEBT: Modify FeedEvent controller, repository and service to generate one FeedEvent per event. | 2 | 2.5
NA | Tasks without a story | 4158 | TECH-DEBT: Resolve error where Header doesn't know which role the user is, so flashes between admin/user header styles | 1.5 | 0.5
NA | Tasks without a story | 4155 | TECH-DEBT: Resolve warnings thrown by JEST Tests over bootstrap-vue elements | 2 | 18.8
NA | Tasks without a story | 4157 | TECT-DEBT: Modify the GET request for FeedEvent(s) to work with the changes to the DB | 2 | 1
424 | U33 - Activity Outcomes | 4357 | Add existByOutcome to ResultRepository and add repository to OutcomeController | 2 | 0.5
424 | U33 - Activity Outcomes | 4328 | Create DELETE endpoint for when deleting an Outcome BACK-END | 3 | 2.5
424 | U33 - Activity Outcomes | 4333 | Create DELETE request for an Outcome when deleting activity FRONT-END | 1.5 | 3.3
424 | U33 - Activity Outcomes | 4327 | Create PUT endpoint for when updating an Outcome BACK-END | 3
424 | U33 - Activity Outcomes | 4332 | Create PUT request for an outcome when editing activity FRONT-END | 3 | 3.3
424 | U33 - Activity Outcomes | 4799 | Fix mutating props warning, refactor prop name. | 1 | 0.2
422 | U35 - Activity search - (Modified ACs) | 4326 | Add activity to the search for drop down | 0.5 | 0
422 | U35 - Activity search - (Modified ACs) | 4329 | Add a text search (UI element) by option to the front end (to enter the name in) | 2 | 0.5
422 | U35 - Activity search - (Modified ACs) | 4790 | Add pagination to backend GET endpoint for searching by keyword | 3 | 1.7
422 | U35 - Activity search - (Modified ACs) | 4337 | Add the method in the backend for searching for a activity by activity type (OR) | 1.5
422 | U35 - Activity search - (Modified ACs) | 4353 | Add the method in the backend for searching for an activity by activity type (AND) | 2.5
422 | U35 - Activity search - (Modified ACs) | 4350 | Add the method in the backend for searching for an activity by name | 3 | 4.5
422 | U35 - Activity search - (Modified ACs) | 4356 | Create card for displaying activity search results | 3 | 4.4
422 | U35 - Activity search - (Modified ACs) | 4741 | Create new component ActivitySearch.vue STUB | 1.5 | 1.5
422 | U35 - Activity search - (Modified ACs) | 4742 | Create new component UserSearch.vue | 3 | 2.1
422 | U35 - Activity search - (Modified ACs) | 4352 | Define the search rules for searching for activities by name | 0.5 | 1
422 | U35 - Activity search - (Modified ACs) | 4355 | Implement the GET request for activities by name on the front end | 3
422 | U35 - Activity search - (Modified ACs) | 4354 | Implement the GET request for activity by activity type on the front end | 2.5
422 | U35 - Activity search - (Modified ACs) | 4789 | Implement the Search Rules into the search by name get endpoint | 3 | 5.9
422 | U35 - Activity search - (Modified ACs) | 4359 | Implement error handling on the front end | 1
422 | U35 - Activity search - (Modified ACs) | 4351 | Update the search by name method to do exact match searches | 3 | 3.5
420 | U37 - Map pane | 4728 | Add LocationIO .vue to ActivityForm.vue (Creating and Editing an Activity) | 2
420 | U37 - Map pane | 4725 | Add LocationIO .vue to EditLocation.vue (Edit user/profile) | 1.5
420 | U37 - Map pane | 4591 | Add MapViewer.vue component to ViewProfile.vue page. | 1.5 | 0
420 | U37 - Map pane | 4726 | Add MapViewer.vue component to ViewActivity.vue page. | 1.5
420 | U37 - Map pane | 4597 | Create 'view-only' option in LocationIO.vue | 2.5 | 1.3
420 | U37 - Map pane | 4582 | Create LocationIO.vue component | 3 | 4.5
420 | U37 - Map pane | 4590 | Create a component MapViewer.vue for only viewing locations on a map (MapViewer.vue) | 3 | 10.4
420 | U37 - Map pane | 4821 | Fix Environment Variable for API Key in GitLab Runner | 1 | 0.8
420 | U37 - Map pane | 4801 | Modify MapViewer to correctly fit to the page it is on (AC1) | 0.5
420 | U37 - Map pane | 4719 | Research how to add a map component to Vue, write business report | 2.5 | 1.2
420 | U37 - Map pane | 4722 | Store the GoogleMaps API key as an environment variable in the front end. | 2 | 1.8
420 | U37 - Map pane | 4583 | Toggle visability of map pane in LocationIO component. (LocationIO .vue) | 2 | 0.5
419 | U38 - User Geolocation - (Modified ACs) | 4580 | In EditProfile.vue, create a new Component EditLocation. Put component in a tab in EditProfile.vue STUB | 2.5 | 1.1
419 | U38 - User Geolocation - (Modified ACs) | 4840 | Add BACK-END UserController endpoint to Edit Location | 3 | 2.4
419 | U38 - User Geolocation - (Modified ACs) | 4729 | Implement EditLocation.vue to use api calls to edit a user's location | 3 | 1.6
419 | U38 - User Geolocation - (Modified ACs) | 4587 | Create Location class on backend. | 3 | 2.9
419 | U38 - User Geolocation - (Modified ACs) | 4846 | Move the location data for test database from the activity table to the location table | 2.5 | 1
419 | U38 - User Geolocation - (Modified ACs) | 4588 | Add fields public_location and private_location to User class | 1.5 | 0.7
419 | U38 - User Geolocation - (Modified ACs) | 4589 | Add Location Details to User Payload. Response | 1.5
419 | U38 - User Geolocation - (Modified ACs) | 4793 | Add my location (public and/or private) pins to the LocationIO component (give to its prop) | 2
419 | U38 - User Geolocation - (Modified ACs) | 4730 | Manually moving a pin to the location you want, will enter an address in the textbox. | 6
421 | U39 - Activity Geolocation | 4712 | Modify the activity class to link to one location object | 1
421 | U39 - Activity Geolocation | 4718 | Modify the activityValidator to check Location objects within activities. BACK-END | 1 | 2.1
421 | U39 - Activity Geolocation | 4713 | Modify ActivityResponse payload to include location. BACK-END | 1
421 | U39 - Activity Geolocation | 4715 | Implement the use of LocationIO within ActivityForm.vue for creating and editing activities | 3
421 | U39 - Activity Geolocation | 4721 | Add my location and activity location pins to the LocationIO component (give to its prop) | 3
450 | U42 Pins - (Modified ACs) | 4735 | Create pin class | 2
450 | U42 Pins - (Modified ACs) | 4239 | Create ActivityService for converting List Activity to List Pin | 3
450 | U42 Pins - (Modified ACs) | 4734 | Create endpoint for getting pin information (in blocks) | 3
450 | U42 Pins - (Modified ACs) | 4720 | Add map pane to all activities page (Using MapViewer.vue component) | 1
450 | U42 Pins - (Modified ACs) | 4731 | Set map to load centered on your location | 0.5
450 | U42 Pins - (Modified ACs) | 4585 | Add pins on the map given their longitube/latitude value (MapViewer.vue) | 2.5
450 | U42 Pins - (Modified ACs) | 4733 | Hover window for pins | 3
450 | U42 Pins - (Modified ACs) | 4732 | Link pins to go to activity detail page when clicked | 1.5
451 | U34 - Activities near me | 4740 | Add sorting to ActivityService for sorting by distance to a location | 2
451 | U34 - Activities near me | 4737 | Add endpoint to ActivityController for searching by location | 3
451 | U34 - Activities near me | 4738 | Add "Location" option to search by dropdown | 1
451 | U34 - Activities near me | 4736 | Add LocationIO.vue to ActivitySearch.vue for inputing location search field for activity | 2
| TOTALS |  |  | 140.5 | 103.6